## Slide 1: Data Verification Current Status and the future plan
SSNP

## Slide 2: Data Verification
  Inhouse development has been done by Social Safety Nets project for the data verification process. Piloting process is in progress in Nuwargampalatha East in Anuradhapura District.
  Total 3,250 families to be verified including Samurdhi, Elderly,Disabled and CKDU
  According to the decision taken at the Project steering Committee held on October 2020, piloting verification process has been initiated.
  29 tablet computers use for the mobile data verification and Gramanildhari and Samadhi Development officer visit the HH and verify the information.

## Slide 3: Lessons Learned
Organization
  Rethinking and Automation current system
  Work units change
Process
  Role Changes
  Improving service and establish process ownership
Technology
  Trust, value for Smart Technology
  Adaptation to the system environment
People
  Jobs change and adaptation
  Officers' roles change
  Empowerment and improvement of capacity

## Slide 4: Lesson Learned continue
Strength
DS Level Management Structure
Weakness
Age and resistance of methodology
Opportunity
Process ownership
Threats
Time
Leadership
Domain Knowledge
Responsibilities and role priority
Spatial Knowledge
Data Validity
Capacity
Changing mindset for new direction
Cost
Partnership
Officers combination

## Slide 5: Implementation plan for 332 DS Divisions
Identify Dedicated two officers including SDO
Provide Equipment
Training
HH Visits and Data Verification
Average Number of HH Per DSD | Number of Dedicated Officers | Number of Tablets Computers Assigned | Average Number of Application per months | Expected Man months for completion 332 DSDs
3,000 | 2 | 2 | 400 | 7.5

## Slide 6: Project Progress after Data verification
Transformation
70%
Implementation
50%
System
20%

## Slide 7: Keep up to date information
Process Designing has been completed
Policy decision
Ownership/Operation/Maintenance
Development of IWMS
Start Development process
Expand into other programs and organizations