## Slide 1: Readiness and the way forward (For next 9 Months)

## Slide 2: Expected Outcome of the Social Safety Nets Project
National Social Protection Strategy
Graduation and Exit
Standardized Targeting System

## Slide 3: Long Term Objective
Sigle Window
(IWMS)
Standardized Targeting System
Service Delivery and Compliance Monitoring System
Government-to-Persons (G2P)
Information Systems and Business Process
Grievance Redress System (GRS)

## Slide 4: Short term Strategic Vision
To provide a mechanism for organizations assisting low-income households/members to structure their support and enable such low-income households/ members to request for additional support from such programs.
Ministry of finance
Program Support
Program Designing
Policy Direction Information
Social Registry/Law income HH Database
National Planning
Financial Management

## Slide 5: Transformation SRIS into IWMS

## Slide 6: Advantages of IWMS
Continuous Registration of Social Welfare Request, providing an Up-to-Date picture of the Low-income Households.
Better Coordination among the Different Social Welfare Programs that support the Low-income Households.
Selection and Enrolment of Eligible Households based on the Available Fiscal Space.
Continuous Monitoring of Progress and Graduation of Registered Beneficiaries.
Capture Support for Low-Income Households by 3rd Party Institutions.
Supporting the Grievances and Handling Queries.

## Slide 7: Next Steps
Activity | Methodology | Start Time | End Time
Upgrade SRIS into IWMS | Hybrid/Inhouse | April | September
Start Data Verification in other 331 DS Divisions | Replicate Pilot Model | April | December
Field Test Beneficiary Selection Method proposed by DCS | Five sample DS results analysis (Urban, Rural, Estate,NE area) | April | June
Awareness creation among all stakeholders / Training | Communication Strategy | April | September
Establish Sustainable Mechanism | Collaborative ‘Three Pillar’ Model | April | May

## Slide 8: Proposed ‘Collaborative 3 Pillar’ Model
Ministry of Finance
Ministry of Samurdhi/ Social Protection
Ministry of Home Affairs

## Slide 9: Our Implementation Strategy

## Slide 10: Stage 2: Deployment plan for 332 DS Divisions
Identify Dedicated two officers including SDO
Provide Equipment
Training
HH Visits and Data Verification
Average Number of HH Per DSD | Number of Dedicated Officers/Tablets per DSD | Ave. Number of Households completed per Day | Average Number of Households per months | Number of Months to Complete a DSD
3,000 | 2 | 10 | 400 | 7.5

## Slide 11: Requirement of Dedicated Institutional Setup within MoF
Strategic Deployment of IWMS with the support of all stakeholder
Awareness creation on value, urgency and policy direction through the MOF
The long-term ownership and continuality and sustainability
Operation and maintenance of the IWMS System should also be considered, as it would eventually include all 23 Social Welfare Programs spanning multiple Ministries and Departments.
DON’T DISCUSS THIS SLIDE NOW

## Slide 12: Our Plan- A

## Slide 13: Our Plan- A