## Slide 1: Data Verification: Current Status & the future plan and Movement to the IWMS
SSNP

## Slide 2: Four Stage Strategy for Supporting Social Safety Net Programs.
1
Initiate: Transfer the Available Electronic Information on to the SRIS System. (Data Migration Routine)
2
Create: Update the Available Electronic Information to 2020 Information. (Field Validation Module)
3
Maintain: Ensure the updated 2020 Information is continuously kept updated. (IWMS System).
4
Expand: Register the balance 20 odd social safety net assistance programs within the IWMS System.

## Slide 3: Stage 1: Initiate - Completed
The SRIS System was verified and accepted.
The signing of the Maintenance Agreement is pending.
Migrated all information available to the Samurdhi Department onto the SRIS System.
At least one officer in 225 DS Divisions have been given an initial training.
An independent verification found up to around 70% completeness of the information.
To increase the completeness to 90% - currently undertaking the verification.

## Slide 4: Stage 2: Data Verification
  The verification module was developed in-house by Social Safety Nets project. (Delays in getting the module from the SW developer)
  Piloting this verification module is in progress at Nuwargampalatha East in Anuradhapura District.
  Total 3,250 families to be verified including Samurdhi, Elderly, Disabled and CKDU and progressing well.
  According to the decision taken at the Project steering Committee held on October 2020, the Eligibility Criteria will be tested using the data of 5 DS Divisions.
  29 tablet computers for the data verification have now arrived and the data verification of the balance DS Divisions would be started immediately.

## Slide 5: Stage 2: Pilot Data Verification Method
Samurdhi Department identifies the appropriate DS Division and informs the Samurdhi Officers of the initiative to undertake the Data Verification within their DS Division.
Through the Ministry of Internal (Home) Affairs the Divisional Secretary is requested to support this initiative.
The SSNP Team visits and undertakes an initial introduction to identify the capabilities and standards of the various officials and appoints a co-ordinator.
Several training sessions were conducted for the different officers.
After the training, teams (2 officials) were sent to capture the data. Each Official are paid an honorarium of Rs. 50/- per household.
Around 10 households are completed by a team per day.

## Slide 6: Stage 2: Lessons Learnt
There is a high degree of enthusiasm to use the digital equipment to gather the data, mainly among the younger officers.
The capacity to undergo training and use the ‘verification module’ varied depending on the specific officer.
The team consisting of the Samurdhi Officer and Gramaniladhari did not raise any suspension among the public. No unwanted discussions were heard among the public in relation to this effort.
The tab was a useful method to capture that data.
The structure of the form and the process was simple enough for most to adopt.
Around 40% of the officials were highly enthusiastic and motivated.

## Slide 7: Stage 2: Deployment plan for 332 DS Divisions
Identify Dedicated two officers including SDO
Provide Equipment
Training
HH Visits and Data Verification
Average Number of HH Per DSD | Number of Dedicated Officers/Tablets per DSD | Ave. Number of Households completed per Day | Average Number of Households per months | Number of Months to Complete a DSD
3,000 | 2 | 10 | 400 | 7.5

## Slide 8: Overall Project Progress after Data verification
Transformation
70%
Implementation
50%
System
20%
Infrastructure
70%

## Slide 9: Stage 3: How to Maintain the Information Up-to-Date
It is necessary to move from the Static Database – which will be obsolete in around 6 months, to maintain the information always accurate and up-to-date.
This would require the implementation of the IWMS (Integrated Welfare Management System).
  The design of the IWMS System was finalized and presented to the PSC.
  Policy decision on the development of the Systems needs approval.
  The long-term ownership, operation and maintenance of the IWMS System should also be considered, as it would eventually include all 23 Social Welfare Programs spanning multiple Ministries and Departments.
  In order to keep the information being collected current – the IWMS development should also start as soon as possible.

## Slide 10: Thank you

## Slide 11: Lessons Learned
Organization
  Rethinking and Automation current system
  Work units change
Process
  Role Changes
  Improving service and establish process ownership
Technology
  Trust, value for Smart Technology
  Adaptation to the system environment
People
  Jobs change and adaptation
  Officers' roles change
  Empowerment and improvement of capacity

## Slide 12: Lesson Learned continue
Strength
DS Level Management Structure
Weakness
Age and resistance of methodology
Opportunity
Process ownership
Threats
Time
Leadership
Domain Knowledge
Responsibilities and role priority
Spatial Knowledge
Data Validity
Capacity
Changing mindset for new direction
Cost
Partnership
Officers combination

## Slide 13: Keep up to date information
Process Designing has been completed
Policy decision
Ownership/Operation/Maintenance
Development of IWMS
Start Development process
Expand into other programs and organizations