## Slide 1: Progress As at 20th March 2021 and the Way Forward
Social Safety Nets Project

## Slide 2: PROJECT DEVELOPMENT OBJECTIVES
To contribute to the improved equity, efficiency and transparency of Sri Lanka’s Social Safety Net programs for the benefit of the poor and vulnerable.

## Slide 3: Project Time Plan

## Slide 4: New DLR Matrix after Restructuring Project Components
DLI | Year | DLR | Value (US$MN) | Progress
DLI 1 | Year 1 | WBB fully functional and its secretariat established | 2.5 | Achieved
 | Year 4 | Welfare Benefits Board fully staffed and conducting regular Board meetings | 1.5 | 
 | Year 5 | Welfare Benefits Board fully staffed and conducting regular Board meetings | 1.0 | 
DLI 2 | Year 1 | SRIS active and SRU maintained with suitably qualified staff | 5.0 | Achieved
 | Year 4 | At least 70% of divisional secretariats have access to the SRIS interface and at least one staff member is trained in its use | 3.0 | Achieved
 | Year 5 | At least 90% of divisional secretariats have access to the SRIS interface and at least one staff member is trained in its use | 2.0 | By November 2021
DLI 4 | Year 4 | Data on 70% of Samurdhi beneficiaries accessible in the Social Registry | 5.0 | Achieved
 | Year 5 | Data on 90% of Samurdhi beneficiaries accessible and updated in the Social Registry | 5.0 | By November 2023
DLI 7 | Year 4 | Samurdhi program scaled up to provide relief to households | 45.0 | Achieved
 |  | Project management and monitoring | 5.0 | On going
 |  | Total | 75.0 | 

## Slide 5: Financial Progress
Original Approved Amount | 75,000,000.00
Current Undisbursed | 11,728,086.01
Disbursed | 64,816,967.99
Financial Progress | 85%

## Slide 6: Expected major outcomes from the social safety nets project
Establish a Welfare Benefits Board (WBB),under the Ministry of Finance (MoF), that will assume management of benefits and payment for all of the country’s social welfare Assistant programs
Integrated Welfare Management System to facilitate entry and updating of beneficiary data and application of the new selection criteria to determine program eligibility. It will provide poverty scores for the distributers
National Social Protection Strategy
Graduation and Exit Strategy

## Slide 7: 1.The way forward to IWMS
Data Migration
Data verification
Maintain Up to date Information
Expand to other Programs

## Slide 8: Stage 1: Initiate/Data Migration - Completed
The SRIS System was verified and accepted.
The signing of the Maintenance Agreement is pending
Migrated all information available with the Samurdhi Department onto the SRIS System.
At least one officer in 240 DS Divisions have been given an initial training.
An independent verification found up to around 70% completeness of the information.
To increase the completeness to 90% - currently undertaking the verification.

## Slide 9: Stage 2: Pilot Data Verification Method
Samurdhi Department identifies the appropriate DS Division and informs the Samurdhi Officers of the initiative to undertake the Data Verification within their DS Division.
Through the Ministry of Internal (Home) Affairs the Divisional Secretary is requested to support this initiative.
The SSNP Team visits and undertakes an initial introduction to identify the capabilities and standards of the various officials and appoints a co-ordinator.
Several training sessions were conducted for the different officers.
After the training, teams (2 officials) were sent to capture the data.
Around 10 households are completed by a team per day.

## Slide 10: Stage 2: Lessons Learnt
There is a high degree of enthusiasm to use the digital equipment to gather the data, mainly among the younger officers.
The capacity to undergo training and use the ‘verification module’ varied depending on the specific officer.
The team consisting of the Samurdhi Officer and Gramaniladhari did not raise any suspension among the public. No unwanted discussions were heard among the public in relation to this effort.
The tab was a useful method to capture that data.
The structure of the form and the process was simple enough for most to adopt.
Around 80% of the officials were highly enthusiastic and motivated.

## Slide 11: Technological and attitudinal Changes
IWMS
The Change in Technology
Adoption of technology by Society
Reduced dependence on Physical Documents

## Slide 12: Overall Project Progress after Data verification
Transformation
70%
Implementation
50%
System
20%
Infrastructure
70%

## Slide 13: 3 (c) National Social Protection Strategy
Current status
A consultantancy firm has been hired to develop the National Social Protection Strategy.
Assessment report has bee reviewed by NPD and to be tabled to the TRC.
Comments to be intergraded from TRC before starting strategy development
NPD will decide the methodology for the development of strategy after given the TRC decision

## Slide 14: Preparation of Graduation and Exit Strategy
Consultant has been appointed to develop Graduation and Exit Strategy.
IT Manager, Training Manager, Communication Manager are also appointed
Assessment report and draft operational manual has been submitted and approved.
Piloting model for selected five GNDs is in progress

## Slide 15: Readiness and the way forward (For next 9 Months)

## Slide 16: Short term Strategic Vision
To provide a mechanism for organizations assisting low-income households/members to structure their support and enable such low-income households/ members to request for additional support from such programs.
Ministry of finance
Program Support
Program Designing
Policy Direction Information
Social Registry/Low income HH Database
National Planning
Financial Management

## Slide 17: Advantages of verified database (SRIS Level)

## Slide 18: Current Scope of the Application in the Mobile App
We collected and mapped 40 application forms in 40 welfare programs currently available.
Digital form was created to capture Social Safety Nets programs/Social Assistant Programs
Information for 17 welfare programs can be captured through the current single digital application

## Slide 19: Advantages of having IWMS for the Government
Receive Request, Verify and Select Low-income Households and Fiscal Space Management.
Selection, Case Management, Enrolment, Progress Monitoring and Graduation of Registered SNAP Beneficiaries.
Capture Support for Low-Income Households
Grievance and Query Handling
Creating Distributors, Assigning Beneficiaries and Distribution of Benefits
Citizen Feedback and Information Sharing Process

## Slide 20: Next Steps
Activity | Methodology | Start Time | End Time
Upgrade SRIS into IWMS | Hybrid/Inhouse | April | September
Start Data Verification in other 331 DS Divisions | Replicate tested Model | April | December
Policy Decision for Beneficiary Selection Methodology | Five sample DS results analysis (Urban, Rural, Estate,NE area) | April | June
Awareness creation among all stakeholders / Training | Communication Strategy | April | September
Establish Sustainable mechanism | Collaborative Model (Three Pillars Support) | April | May

## Slide 21: Our Implementation Plan for next steps

## Slide 22: Proposed ‘Collaborative 3 Pillar’ Model
Ministry of Finance
Ministry of Samurdhi/Social Protection
Ministry of Home Affairs

## Slide 23: Stage 2: Deployment plan for 332 DS Divisions
Identify Dedicated two officers including SDO
Provide Equipment
Training
HH Visits and Data Verification
Average Number of HH Per DSD | Number of Dedicated Officers/Tablets per DSD | Ave. Number of Households completed per Day | Average Number of Households per months | Number of Months to Complete a DSD
4,000 | 2(2*332=664) | 10 | 400 | 10

## Slide 24: Activities to be started immediately
Start training of WBIU (TOT) officers at DS Divisional level
One Laptop has been provided 2018 to each DS and to be used for training sessions
WBIU officers to be started verification module training for GN, EDO, SDO and any other dedicated officers
DS level team will be trained by may 30th
25 model DS Divisions to be established covering 25 Districts.

## Slide 25: Action Plan
No | Activity | Timeline
01 | Commencement of procurement for Tabs | April 2021
02 | Delivery of Tabs | August 2021
03 | Initial Discussion with DS and relevant Staff | April & May 2021
04 | Appoint the project team in DSD level | April & May 2021
05 | Conduct awareness programs and distributing IEC materials | April , May, June & July 2021
06 | Conduct Technical Training programmes | April , May, June & July 2021
07 | Data Collection by data entry officers | 10 Months
08 | Monitoring | Throughout the Project
09 | Project Closer and document Lessons learned | January 2022